## Sheet1
List of pointes to be closed on A-LCA Working Document [ ]
section | title | [ ] | Status during 27th IWG meeting | who | what | by when | proposed text or the current status as of October 8 | After October 8th meeting Decisions | reference document | as of 93rd GRPE | JPN positions <draft> | Justifications | OICA positions
all |  | light duty vehicle | agreed with "LDV" the modified text for functional unit is expected to be present during 28th IWG meeting (October 8th) | SG4 | consult with the relevant member and develop the compromised text for FU, then sent to IWG leading team | 2025-10-03 | for functional unit, please refer III 7.5. |  | A-LCA-28-09e_GRPE-2025-17 Draft ID_SG4.docx | CLOSED | support "light duty vehicle" instead of "passenger car" including the modification of functional unit please refer A-LCA-26-06r1e
|  | phase vs stage | CLOSED with "stage" for each life cycle |  | DONE |  |  |  |  | CLOSED | please refer A-LCA-26-07e
| Inconsistency in equations |  | newly proposed | OICA | propose the solution and send to the relevant SG | 2025-10-03 | no action is taken | to be concluded IWG 29th meeting | Microsoft Excel Spreadsheet A-LCA-27-08e_OICA_UNECE A-LCA method TEST formula.xlsx |  |  |  | A-LCA-27-06e A-LCA-27-08e
III 1.1. | Purpose and principles | and verification |  | IWG | will make a decision on 10/8 | 2025-10-08 | Leading Team Decision remove [ ] | remove [] adopted |  | CLOSED | keep "and verification"(Japan comment) | concern on cheating without verification
III 3. | Definitions |  |  | SG7 | DONE |  | several [ ]s remain | skipped |  |  | basic idea : no terminology or well described in the text→delete、inconsistant with the text→modify or delete concrete proposals : later
III 7.1 | Level Concept | texts in [ ] | CLOSED except USE stage in blue highlighted portions final confirmation on A-LCA-26-04r1e_GRPE-2025-17 Draft ID_Level Concept after 26th Mtg.docx including the proposal made by SG2 confirm the final modification within 27th A-LCA-27-10e | SG3 SG7 | under the progress |  | close to finalisation by SG7 with huge support from Song-san | skipped
Figure 1
Figure 2
|  | Table 1 | [5 empty] | [] to be modified after SGs update | (reference)_251006_clean GRPE-2025-17 Draft Informal Document.docx
III 7.3 | Hotspots | texts in [ ] |  |  |  |  | designated group proposal : A-LCA-28-03e OICA input : A-LCA-28-03e |  |  |  | tbd |  | A-LCA-27-07e
|  | Figure 3 (bottom table) | the designated group* is set to develop the compromised proposals * : USEPA/France/SG3/OICA next action : IWG leading team will organise the | A-LCA leading team | consult with the relevant member and develop the compromised text | 2025-10-03 |  | Maintain original 3.33 with OICA additional text. 7.3 should be kept but moved to another part of MR because it's general information. Hotspot to be further developed in IWG 29 US EPA to lead discussion week 41 with JPN, OICA, EU COM, CLEPA | (reference)_251006_clean GRPE-2025-17 Draft Informal Document.docx (reference)_251006_clean GRPE-2025-17 Draft Informal Document.docx | [ ] still open text will be submited to leading team by 10/13 | All life cycle [stages] collectively contributing more than 50% to any impact category. With this definition, one specific process contributing 49% of impact within a certain life phase may not be pursued as a “Hot spot”? should be consider per each life cycle stage considering the consistency with cut-off rule [50%] is still open |  |  | Hotspot means a certain process which emits higher amount of GHG exceeding the average in a certain boundary condition.
III 7.5 | Functional Unit and reference flow | texts in [ ] | [ ] waiting for SG4 meeting outcome | SG4 | consult with the relevant member and develop the compromised text, then sent to IWG leading team | 2025-10-03 | A-LCA-28-09e | to be forwarded to SG7 | A-LCA-28-09e_GRPE-2025-17 Draft ID_SG4.docx | Member should provide the comments and/or feedbacks to IWG by 10/14 | please refer A-LCA-26-06r1e
III 7.8 | Land Use Change | texts in [ ] | (SG6) | SG6 | provide the SG6 decision to IWG leading team | 2025-10-03 |  | CP meeting before 29th IWG |  | [ ] still open discussion table will be uploaded to wiki | no strong position |  | A-LCA-27-07e
III 7.9 | Representative vehicle (RV) Determination | texts in [ ] | 1. definition of upstream group criteria is expected to be present during 28th IWG meeting 2. need further explanation to US/JRC for better understanding | SG3 | develop the compromised text based on the agreement with the relevant member (currently USEPA is arranging the designated meeting) | 2025-10-03 | new proposal is under the review by the designated group (meeting data : tbd) | meeting with OICA JPN, JRC, US EPA before 29th IWG | A-LCA-28-11e_GRPE-2025-17 Draft ID_RV.docx | [ ] still open basic concept was shared to US/EC the latest text is shared within IWG as A-LCA-28-11e review by 10/27 and provide the comments and/or feedbacks no feedback means that "accepted" | please refer the sheet ”RV” and please refer A-LCA-28-11
III 7.9.2 | RV: Selection | the highest configuration of a vehicle | [8 empty] | not acceptable please refer A-LCA-26-08e/09e | avoid cheating
III 7.9.3.1. | Definition of Upstream LCA Group | (a) | [8 empty] | delete all and describe (reserved) at this stage please refer A-LCA-26-08e/09e | current criteria makes no sense. Please refer the sheet "RV". No concrete counter-proposal is available | A-LCA-27-07e
(b)
(c)
(d)
III 7.9.6.1. | Definition of EoL LCA group | [9 empty] | delete all and describe (reserved) at this stage please refer A-LCA-26-08e/09e
III 7.12. | Data collection requirements and data types |  | keep as it is with [ ] | SG3 | consult with the relevant member and develop the compromised text, then sent to IWG leading team | 2025-10-03 | under the discussion within SG3 and relevent member |  |  | the reviced text is ready on 10/14 within IWG (29th wiki) deadline of comments : 10/27
|  | Table 2 | [8 empty] | Use and EoL should be added in the same manner of material and production should include Use and EoL stages
III 7.12.1. | Data quality | most | keep as it is with [ ] | [8 empty] | ambiguous
III 7.12.2. | Primary data share | 50% | keep as it is with [ ] |  |  |  |  | before 29th IWG CP & SG4 to confirm or reject 50% PDS in production SG3 to provide updated text to A-LCA leading team for distribution to IWG wiki |  |  | oppose(Japan comment) not acceptable | 1. may disturb decarbonisation in some cases (original text mentioned, but seem to be intentionally deleted) 2. waste a ton of resources to determine and/or track so many materials and parts with no contribution on decarbonisation. these resources should be utilise the real decarbonisation 3. leads to kick out the small manufacture from market. against the economic principle and customer benefit 4. industry accelerate the primary data usage to pursue their product without PDS 5. make no sense as a methodology | A-LCA-27-06e A-LCA-27-07e |  | PDS=33%? | 78.4% | real world FE = xx L/km（P） * 1.25（descrepancy_S） * 1.02（deterioration_S）
[15 empty] | PDS=67%? | 98% | real world FE = xx L/km（P） * 1.25（descrepancy_P） * 1.02（deterioration_S）
III 7.13. | Cut-off rule | 3% | keep as it is with [ ] | Leading Team | provide the Leading Team decision and gather IWG member feedbacks | 2025-10-03 | Leading Team Decision remove [ ] no proposal other than JPN | [] to be removed |  | CLOSED | ok(Japan comment) acceptable
III 7.14. | Screening Analysis |  | waiting for OICA input by 24th September | OICA SG3 | OICA provide their concerns to SG3, then SG3 develop the compromised text | 2025-10-03 | no action is taken | OICA to respond to CLEPA to explain concerns before 29th IWG |  | OICA provide the modified text by 10/27 |  |  | A-LCA-27-07e
III 7.15.2. | Electricity modelling | [The inclusion of such upstream elements should be prioritised ....] | in progress | SG6 | provide the SG6 decision and inform IWG leading team of their decision | 2025-10-03 |  | CPs request to respond to SG6 leaders and next meeting still to be scheduled COM to present COM view on IWG 29 meeting and Wiki US to organise meeting with CPs Week 41 |  | [ ] still open discussion table is shared within SG6 deadline 10/26 | no strong position | can be deleted since defined in the other section
III 7.15.2.1. | Electricity from the grid via a contractual instrument | • [Mixing location-based and market-based modelling shall be avoided within one life cycle [stage] of an LCA]. | in progress | [9 empty] | A-LCA-27-07e
|  | [The entity shall document in the carbon neutrality management plan...] | in progress | [8 empty] | no strong position
III 7.16.2.4 | Multi-output allocation | economic value ratio is equal to or lower than five | keep as it is with [ ] | SG3 | consult with the relevant member and develop the compromised text, then sent to IWG leading team | 2025-10-03 | under the discussion with SG3 and relevent member | CPs invited to check text before 29th IWG. SG3 request to provide justification and examples to be shared with A-LCA IWG leading team |  |  |  | not acceptable The decision to adopt physical or economic allocation is based on the economic ratio, though this is not an ISO rule. ISO simply prioritizes allocation methods based on physical relationships (e.g., weight), followed by other relationships (e.g., economic value). The A-LCA methodology should follow this order as well. Consequently, Figure 12 and the related text must be amended.
|  | If physical relationships are not used, the validity of the allocation method used in the study should be demonstrated | keep as it is with [ ] | [7 empty] | OK to delete [ ] (support the text) | proposed by Japan (follow ISO rule)
III 7.17. | Chain of custody |  | Next actions : IWG leading team will invite CP for their concrete position (items not to be supported,,,) until 28th IWG meeting text : additional texts need to be readable JPN/CLEPA and US provide the concrete text proposals, then come back for further discussion on Day2 waiting for counter-proposal on A-LCA-26-05e come back at 14:30CET for integrated document by US/JPN/CLEPA | SG2 SG3 | consult with the relevant member and develop the compromised text, then sent to IWG leading team | 2025-10-03 | new text was developed for IWG review A-LCA-28-03e | Content confirmed by IWG. Draft to be updated and shared with SG7 | A-LCA-28-08e_GRPE-2025-17 Draft ID_SG7_CoC_Modified_d5.docx |  | please refer A-LCA-28-08e_GRPE-2025-17 Draft ID_SG7_CoC_Modified_d5 | one of major contributors for green washing
III 7.18. | Waste treatment, disposal and recycling modelling | GHG emissions shall be calculated… | CLOSED with A-LCA-27-05e | Leading Team | confirm the A-LCA-27-05e document and upload the document | 2025-10-03 | need to be implemented into the Informal Document (delete text and [ ] ) | [] removed and closed |  |  |  |  | A-LCA-27-06e A-LCA-27-07e
III 8.1. | [12 empty] | A-LCA-27-07e
III 8.1.6. | Energy modelling | For the general rules reference is made to paragraph 3.2.15. In case of electricity supply from the grid and marked based energy modelling (Level 4 & hotspots in Level 3) the following rules shall apply: • If no contractual instruments are applied the residual electricity mix shall be used if available. • If no residual grid mix is provided, secondary data shall be applied reflecting the country specific grid mix. For Level 3 and partially Level 4 the risk of double counting cannot...] | (SG6) | SG6 | consult with the relevant member and develop the compromised text, then sent to IWG leading team | 2025-10-03 |  |  |  |  | support original text | For general rules refer to paragraph 3.2.15. 4.1.4.1. Energy Mix Practitioners shall account for the fuel or electricity production pathways associated with the production locations of each material. (detailed methodology shall be considered) The energy mix shall be based on the latest dataset associated with the location or region of production in question. The methods described in paragraph 3.2.8. shall guide the modelling of fuel and electricity for these regions.
III 8.2. |  |  | (SG3) | OICA | provide the concrete proposal to the relevant SG | 2025-10-03 | no action is taken | to be solved. Text to be shared with IWG A-LCA leading team > to SG 7 |  |  |  |  | A-LCA-27-07e
III 8.2.1.1. | Level 1 |  | (SG3) | SG3 |  |  | no action is taken | to be solved. Text to be shared with IWG A-LCA leading team > to SG 7
III 8.2.1.3. | Level 3 |  | (SG3) | SG3 |  |  | no action is taken | to be solved. Text to be shared with IWG A-LCA leading team > to SG 7
III 8.3. |  |  | (SG4) | OICA | provide the concrete proposal to the relevant SG | 2025-10-03 | no action is taken | [5 empty] | A-LCA-27-07e
III 8.4.] | [Service life/Vehicle activity] and functional unit |  | (SG4) | SG4 | consult with the relevant member and develop the compromised text, then sent to IWG leading team | 2025-10-03 | A-LCA-28-09e | Closed | A-LCA-28-09e_GRPE-2025-17 Draft ID_SG4.docx
III 8.3.1.1. | Service life: methodology and guideline | can indicate a shorter service life supported by primary data, which will lead to a more stringent functional unit | (SG4)
III 8.3.3. | Use phase consumption | OEM-specific average data may be used to determine the “Discrepancy factor” | (SG4) | [7 empty] | not acceptable (JPN has already provided the counter-proposals) | OEM specific factor may lead cheating
powertrains with two modes of operation
III 8.3.3.1. | Calculation of ‘Discrepancy Factor’ | Table 13 | (SG4) | [7 empty] | not acceptable (JPN has already provided the counter-proposals) | OEM specific factor may lead cheating
III 8.3.3.2. | Calculation of ‘Deterioration Factor’ |  | (SG4) | [7 empty] | not acceptable (JPN has already provided the counter-proposals) | technically make no sense to distinguish between discrepancy and deterioration under the current OBFCM accuracy
III 8.3.5.1. | Future Changes in Energy Mix: | a static scenario may be used only where a dynamic scenario is not available | (SG4) | [7 empty] | allow Static？
|  | future scenarios issued… | [8 empty] | no strong position
III 8.3.5.2. | Use phase electricity: |  | (SG4) | [7 empty] | no strong position | delete reinstate）
III 8.3.6.2. | Maintenance carbon emission estimation | Methodology for calculating the need for traction battery replacement(s) | (SG4) | [7 empty] | not acceptable (JPN has already provided the counter-proposals) | depend on reality in the market
|  | Methodology for calculating the need for fuel cell system replacement(s)] | [8 empty] | not acceptable (JPN has already provided the counter-proposals) | depend on reality in the market
III 8.4. |  |  | (SG5) | OICA | provide the concrete proposal to the relevant SG | 2025-10-03 | no action is taken | solved |  |  |  |  | A-LCA-27-07e
III 9. | Reporting |  | CLOSED on SG2/3/5 portions more discussion is necessary for other portions and should be reviewed during the 28th IWG meeting | Leading team | consult with SG3/4 and provide the compromised text to IWG member | 2025-10-03 | A-LCA-28-09e need to be revised per CoC modification | Updated text to be provided by IWG29 with COC changes | A-LCA-28-05e_GRPE-2025-17 Draft ID_Reporting for SG2_3_4_5.docx |  | please refer please refer A-LCA-26-03e
III 10. | Verification process | For Level 3 and 4, the verification … | waiting for OICA input by 24th September | OICA | provide the concrete proposal to the relevant SG | 2025-10-03 | A-LCA-28-10e OICA input for IWG review | Delete [] text to be forwarded to SG7 | Microsoft Word Document A-LCA-28-10e_GRPE-2025-17 Draft ID_Verification.docx |  |  |  | A-LCA-27-07e
In the case that no verification body…

## RV
| Upstream & EoL LCA Group (1) |  | Downstream LCA Group (2)
definitions | (0) exclide traction battery |  | WLTP | CFR
determine per each battery configulation
|  | （ex：40kW/60kW battery of model A need to be determined separately) | refer GTR#15 | refer CFR?
(1)と(2)を統合して素材構成比とする。その場合、group分けの閾値設定は困難 | (1) 鉄のfactor (xx CO2eq/kg)違い
（例：同一モデルでも係数が違えば別group）
（例：Battery除外したNissan Leafはひとつの対象物）
(2) 影響度の高い素材 and/or 製造工程別
貴金属/レアアース等？
(3) パワトレ？
ICEは同じGroup
FCは別Group？
MT/AT/CVT分ける？
facorが更新されたら別Group
一方、(1) & (2)はworse factorでbetter factorカバー可能
（例：向上しても旧factor使用可能）
RV | heaviest weight configuration |  | V_H per IP family | worst conf. per test group |  | RV : heaviest conf. under Group(1), follow each region homologation scheme under Group(2)
Declared Vehicle (DV) | applicable to V_H only (WLTP) |  | V_ind | NA |  | DV : allow only V_H or worst conf. of Group (2) within same Group(1)
| or worst conf. only (CFR) |  |  | (基本１test groupにはひとつの値） |  | （if no restriction, it may lead cheating）
DV with multiple LCA values within same Group(2) : weighted per sales volume ?
(sample)
Nissan Leaf |  | LCA Group(1)_X | RV：
|  |  | Upstream & EoL | traction battery | Use
[5 empty] | WLTP |  | CFR
V_L |  |  | ↓ | ↓ | abc |  | ↓
|  |  | ↓ | ↓ | bcd |  | ↓
|  |  | ↓ | ↓ | cde |  | ↓
V_H |  |  | DV （RVから重量按分計算） | 40kWh | def |  | ijk
|  |  | ↑ | ↑ | efg |  | ↑
V_L |  |  | ↓ | ↓ | fgh |  | ↓
|  |  | ↓ | ↓ | ghi |  | ↓
V_H |  |  | DV （RVから重量按分計算） | 60kWh | hij |  | jkl
同一LCA Group(1)
Group (1)_A
Group (1)_B
Group (1)_C
Group (2) _a
Group (2) _b
Group (2) _c
Group (2) _d
Group (2) _e
RV
RV
RV
DV
DV
DV
DV
DV
DV
DV
according to the RV concept,
key element is weight dependency (interpolated per weight)
１．exclude non-weight dependency
only battery?
２．same group should have same slope per weight３．not practical to consider all materials and parts
focus on impact material and/or parts and/or
process

## timeline
|  |  |  | October, 2025 |  |  |  |  | March, 2026
|  | 2025-07-22 |  | 93rd GRPE |  | 2025-12-12 | end of 2025 |  | WP.29 | 94th GRPE
Current | Mandate
GRPE Approval
WP.29 Approval
Reviced Plan | Case_1
| Mandate | [5 empty] | no need to change the mandate
| GRPE Approval |  |  |  |  | WD deadline |  |  |  | ToR needs to be modified
| WP.29 Approval | [9 empty] | November, 2026
Case_2
| Mandate | [7 empty] | Mandate needs to be modified
| GRPE Approval | [7 empty] | update WD by ID | ToR needs to be modified
| WP.29 Approval | [9 empty] | November, 2026
Case_3
| Mandate | [5 empty] | no need to change the mandate
| GRPE Approval |  |  | with reserved on some parts
| close "reserved parts" |  |  |  |  | WD deadline |  |  |  | ToR needs to be modified
| WP.29 Approval | [9 empty] | November, 2026
EU guideline
X year extention
[7 empty] | finalise the first stage activities |  | develop second activities like testing
| GRPE Approval |  |  | NONE | [5 empty] | with no reserved parts
submit ID reflected the latest situation
or submit ID reflected only agreed items
[6 empty] | close the open items* |  |  | items can be taken care in second phase and by when
[5 empty] | * | energy modeling |  |  |  | representaative vehcile (detail)
hotspot
representaative vehcile (concept)
date quality and primary data share
use stage
|  |  | EC | no text available to be voted @ 93rd GRPE
US
JPN